## HIF1 costs
Updating HIF1 costs for inflation and higher contingency
| A | Methodology
This workbook adjusts the OCC's estimates of HIF1 costs to reflect the latest construction inflation estimates, based on the BCIS TPI index.
We first remove the OCC's inflation assumptions. Next, we overlay the inflation rates based on the BCIS TPI index.
We also calculate the amount of contingency that the OCC provides, and re-calculate the costs for the P80 level (usually what is assumed in large projects), and also the P90/P95.
| B | Results
Impact of inflation
|  | Section |  | HIF1 budget | Forecast | Additional amount required | % difference
|  | A | £000s | 33500 | 37366.4772 | 3866.4772 | 11.54%
|  | B | £000s | 57200 | 63944.5165 | 6744.5165 | 11.79%
|  | C | £000s | 160000 | 179272.749 | 19272.749 | 12.05%
|  | D | £000s | 44801 | 50044.9263 | 5243.9263 | 11.7%
|  | E | £000s | 655 | 698.641 | 43.641 | 6.663%
|  | Overall | £000s | 296156 | 331327.3099 | 35171.3099 | 11.88%
|  | Inflation allowance in HIF1 | £000s | 26653
|  | Additional inflation allowance required | £000s | 35171.3099
|  | Likely inflation allowance required | £000s | 61824.3099
|  | Inflation uplift by section, at P62 level of contingency |  |  | Same table as left, but transposed
|  | Section | £m
|  | A | 6.7299 |  | Section | A | B | C | D | Inflation funding required | Inflation funding available
|  | B | 11.8192 |  | £m | 6.7299 | 11.8192 | 34.0372 | 9.178 | 61.8243 | 26.653
|  | C | 34.0372
|  | D | 9.178
|  | Total | 61.8243
Impact of inflation + risk assumptions
|  | Degree of certainty | Available funding (pre-inflation) | P62 | P80 | P90
|  | £m | 296.156 | 331.3273 | 365.9131 | 402.7715
| C | Stripping out the inflation profile
Profile of spend over time
Table 1 HIF1's spend profile as of revised grant determination agreement
Source: Email from Greg O'Broin, Jan 19 2023, 6:21pm
|  | Section |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | Total | %
|  | A | £000s | 2918 | 750 | 4300 | 10800 | 13900 | 832 | 33500 | 11.31%
|  | B | £000s | 3234 | 750 | 5500 | 22500 | 23100 | 2116 | 57200 | 19.31%
|  | C | £000s | 6373 | 1400 | 10500 | 60000 | 73500 | 8227 | 160000 | 54.03%
|  | D | £000s | 2932 | 700 | 6900 | 12900 | 19200 | 2169 | 44801 | 15.13%
|  | E | £000s | 2022: 637; 2027: 18 | 655 | 0.2212%
|  | Overall | £000s | 16094 | 3600 | 27200 | 106200 | 129700 | 13362 | 296156 | 100%
|  | Overall (£m) | £m | 16.094 | 3.6 | 27.2 | 106.2 | 129.7 | 13.362
|  |  |  | 5.434% | 1.216% | 9.184% | 35.86% | 43.79% | 4.512%
|  |  |  | 5.434% | 6.65% | 15.83% | 51.69% | 95.49% | 100%
Allowance for inflation in HIF1
Source: Amendments to the Grant Determination Agreement, 15 March 2022, paragraphs 25-27.
|  | Inflation | £000s | 2022: 26653
Calculate deflated spend profile
Explanation: to strip out the impact of inflation over time, we assume that the OCC has applied a constant inflation rate over time
To calculate this assumed inflation rate, we use the goal-seek function in Excel. We set the 'goal-seek inflation allowance' cell to 0 by changing the 'goal-seek inflation rate' cell.
|  | Goal-seek inflation rate |  | 2022: 2.251%
|  | Year |  | 1 | 2 | 3 | 4 | 5 | 6
|  | Inflation factors |  | 1.0225 | 1.0455 | 1.0691 | 1.0931 | 1.1178 | 1.1429
|  | Deflated spend profile | £000s | 15739.6263 | 3443.2087 | 25442.5224 | 97150.7593 | 116035.8209 | 11691.0627
|  | Goal-seek inflation allowance | £000s | 2.251% 1: -0.00030772
|  | Inflation factor assumed by OCC |  | 1.0225 | 1.0455 | 1.0691 | 1.0931 | 1.1178 | 1.1429
Table 2 HIF1's deflated spend profile
|  | Section |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | Total | %
|  | A | £000s | 2853.7486 | 717.3351 | 4022.1635 | 9879.7382 | 12435.6046 | 727.9572 | 30636.5472 | 11.37%
|  | B | £000s | 3162.7906 | 717.3351 | 5144.6277 | 20582.788 | 20666.3644 | 1851.3912 | 52125.297 | 19.34%
|  | C | £000s | 6232.673 | 1339.0256 | 9821.562 | 54887.4346 | 65756.614 | 7198.2019 | 145235.511 | 53.89%
|  | D | £000s | 2867.4403 | 669.5128 | 6454.1693 | 11800.7984 | 17177.2379 | 1897.7634 | 40866.9222 | 15.16%
|  | E | £000s | 622.9739 | 0 | 0 | 0 | 0 | 15.7491 | 638.723 | 0.237%
|  | Overall | £000s | 15739.6263 | 3443.2087 | 25442.5224 | 97150.7593 | 116035.8209 | 11691.0627 | 269503.0003 | 100%
Calculate deflated spend profile
Construction inflation as measured by the BCIS TPI
Source: BCIS (2023), 'Construction inflation: is the worst really over', September, slide 10.
|  |  |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2026
|  | Construction inflation rate (%) as measured by BCIS TPI |  | 8.8458 | 5.179 | 2.741 | 3.7778 | 3.4175 | 3.4175
|  | Construction inflation index (BCIS TPI) |  | 1.0885 | 1.0518 | 1.0274 | 1.0378 | 1.0342 | 1.0342
|  | Construction inflation factor (BCIS TPI) |  | 1.0885 | 1.1448 | 1.1762 | 1.2206 | 1.2624 | 1.3055
Table 3 HIF1's spend profile with BCIS TPI construction inflation
|  | Section |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | Total | %
|  | A | £000s | 3106.184 | 821.2259 | 4730.9027 | 12059.6302 | 15698.1867 | 950.3476 | 37366.4772 | 11.28%
|  | B | £000s | 3442.5631 | 821.2259 | 6051.1547 | 25124.2296 | 26088.3535 | 2416.9898 | 63944.5165 | 19.3%
|  | C | £000s | 6783.9996 | 1532.9549 | 11552.2044 | 66997.9455 | 83008.3975 | 9397.247 | 179272.749 | 54.11%
|  | D | £000s | 3121.0869 | 766.4775 | 7591.4486 | 14404.5583 | 21683.8263 | 2477.5287 | 50044.9263 | 15.1%
|  | E | £000s | 678.0806 | 0 | 0 | 0 | 0 | 20.5604 | 698.641 | 0.2109%
|  | Overall | £000s | 17131.9143 | 3941.8841 | 29925.7103 | 118586.3636 | 146478.764 | 15262.6735 | 331327.3099 | 100%
|  | Inflation uplift |  | 2022: 122.9%
| D | Contingency
RCF table
Source: DfT (2021), 'TAG: optimism bias workbook', 19 May, https://www.gov.uk/government/publications/tag-optimism-bias-workbook
UK Road Cost | bar: 2022 to 2024
|  | P-value | Level of certainty of the estimate | 2022: Roads (FBC); 2023: Roads (OBC); 2024: Roads (SOC)
|  | 5 | 5% | 2022: -7%; 2023: -16.82%; 2024: -16.82%
|  | 10 | 10% | 2022: 1%; 2023: -8.824%; 2024: -8.824%
|  | 15 | 15% | 2022: 3%; 2023: -2.825%; 2024: -2.825%
|  | 20 | 20% | 2022: 5.105%; 2023: 2.149%; 2024: -1.64%
|  | 25 | 25% | 2022: 7%; 2023: 7%; 2024: 4.27%
|  | 30 | 30% | bar: 2022 to 2024
|  | 35 | 35% | 2022: 11%; 2023: 11%; 2024: 11%
|  | 40 | 40% | 2022: 13.4%; 2023: 13.4%; 2024: 13.4%
|  | 45 | 45% | 2022: 16%; 2023: 16%; 2024: 16%
|  | 50 | 50% | 2022: 18%; 2023: 18%; 2024: 18%
|  | 55 | 55% | 2022: 20.55%; 2023: 20.55%; 2024: 20.55%
|  | 60 | 60% | 2022: 23%; 2023: 23%; 2024: 23%
|  | 65 | 65% | 2022: 25.65%; 2023: 25.65%; 2024: 39.19%
|  | 70 | 70% | 2022: 29%; 2023: 29.8%; 2024: 41.51%
|  | 75 | 75% | 2022: 33%; 2023: 43.65%; 2024: 76.88%
|  | 80 | 80% | 2022: 37%; 2023: 53.6%; 2024: 98.15%
|  | 85 | 85% | 2022: 40.85%; 2023: 57.78%; 2024: 103.8%
|  | 90 | 90% | 2022: 50.8%; 2023: 69.98%; 2024: 227.3%
|  | 95 | 95% | 2022: 66.92%; 2023: 86.1%; 2024: 243.4%
|  | N |  | 2022: 202; 2023: 202; 2024: 202
|  | Mean |  | 2022: 20.16%; 2023: 22.91%; 2024: 45.77%
Contingency assumed by OCC
|  | HIF1 costs | £000s | 2022: 296156
|  | Inflation allowance | £000s | 2022: 26653
|  | Quantified Risk and Contingency fund | £000s | 2022: 52251; 2023: Source: Amendments to the Grant Determination Agreement, 15 March 2022, paragraphs 25-27.
|  | HIF1 costs excluding inflation and contingency | £000s | 2022: 217252; 2023: RCF uplifts are applied on real values. So we use real HIF costs as a starting point.
|  | Contingency allowed for by OCC |  | 2022: 24.05%
P-value assumed by OCC
|  | P-value |  | 2022: Contingency
|  | 60 |  | 2022: 23%
|  | 65 |  | 2022: 25.65%
|  | P-value assumed by the OCC |  | 2022: 61.9828
Contingency assuming P80/P90/P95
|  | HIF1 costs excluding inflation and contingency | £000s | 2022: 217252
|  | P-value |  | Contingency (%) | Contingency (£) | Extra contingency needed | HIF1 costs (with BCIS TPI inflation) | Inflation allowance
[5 empty] | £000s | £000s | £000s | £000s
|  | 61.9828 |  | 24.05% | 52251 | 0 | 331327.3095 | 61824.3095
|  | 80 |  | 37% | 80383.24 | 28132.24 | 365913.1189 | 68277.8789
|  | 90 |  | 50.8% | 110364.016 | 58113.016 | 402771.5206 | 75155.5046
|  | 95 |  | 66.92% | 145385.147 | 93134.147 | 445826.5409 | 83189.3939
END

## bcis tpi
Data extracted using https://www.graphreader.com/ from slide 10 of : https://bcis-production-2021.s3.eu-west-2.amazonaws.com/2023/09/Construction-Outlook_Final-slide-deck-no-video.pdf
Column1 | Column2 | Year | Quarter | Date | Inflation rate assumed by OCC
1 | 4.946 | 2007 | 1 | 2007Q1 | 2.2515
2 | 4.402 | 2007 | 2 | 2007Q2 | 2.2515
3 | 8.64 | 2007 | 3 | 2007Q3 | 2.2515
4 | 8.177 | 2007 | 4 | 2007Q4 | 2.2515
5 | 4.371 | 2008 | 1 | 2008Q1 | 2.2515
6 | 2.684 | 2008 | 2 | 2008Q2 | 2.2515
7 | -0.88 | 2008 | 3 | 2008Q3 | 2.2515
8 | -4.445 | 2008 | 4 | 2008Q4 | 2.2515
9 | -10.357 | 2009 | 1 | 2009Q1 | 2.2515
10 | -12.522 | 2009 | 2 | 2009Q2 | 2.2515
11 | -12.078 | 2009 | 3 | 2009Q3 | 2.2515
12 | -11.634 | 2009 | 4 | 2009Q4 | 2.2515
13 | -6.302 | 2010 | 1 | 2010Q1 | 2.2515
14 | 0.922 | 2010 | 2 | 2010Q2 | 2.2515
15 | 1.712 | 2010 | 3 | 2010Q3 | 2.2515
16 | 3.966 | 2010 | 4 | 2010Q4 | 2.2515
17 | 4.682 | 2011 | 1 | 2011Q1 | 2.2515
18 | 2.186 | 2011 | 2 | 2011Q2 | 2.2515
19 | 0.746 | 2011 | 3 | 2011Q3 | 2.2515
20 | 1.209 | 2011 | 4 | 2011Q4 | 2.2515
21 | -1.192 | 2012 | 1 | 2012Q1 | 2.2515
22 | 2.562 | 2012 | 2 | 2012Q2 | 2.2515
23 | 1.442 | 2012 | 3 | 2012Q3 | 2.2515
24 | 1.32 | 2012 | 4 | 2012Q4 | 2.2515
25 | 8.594 | 2013 | 1 | 2013Q1 | 2.2515
26 | 2.958 | 2013 | 2 | 2013Q2 | 2.2515
27 | 4.239 | 2013 | 3 | 2013Q3 | 2.2515
28 | 6.529 | 2013 | 4 | 2013Q4 | 2.2515
29 | 5.893 | 2014 | 1 | 2014Q1 | 2.2515
30 | 9.652 | 2014 | 2 | 2014Q2 | 2.2515
31 | 10.59 | 2014 | 3 | 2014Q3 | 2.2515
32 | 8.374 | 2014 | 4 | 2014Q4 | 2.2515
33 | 7.714 | 2015 | 1 | 2015Q1 | 2.2515
34 | 5.145 | 2015 | 2 | 2015Q2 | 2.2515
35 | 5.257 | 2015 | 3 | 2015Q3 | 2.2515
36 | 4.331 | 2015 | 4 | 2015Q4 | 2.2515
37 | 3.601 | 2016 | 1 | 2016Q1 | 2.2515
38 | 3.797 | 2016 | 2 | 2016Q2 | 2.2515
39 | 3.901 | 2016 | 3 | 2016Q3 | 2.2515
40 | 7.731 | 2016 | 4 | 2016Q4 | 2.2515
41 | 9.309 | 2017 | 1 | 2017Q1 | 2.2515
42 | 8.947 | 2017 | 2 | 2017Q2 | 2.2515
43 | 8.96 | 2017 | 3 | 2017Q3 | 2.2515
44 | 8.911 | 2017 | 4 | 2017Q4 | 2.2515
45 | 8.28 | 2018 | 1 | 2018Q1 | 2.2515
46 | 6.332 | 2018 | 2 | 2018Q2 | 2.2515
47 | 6.491 | 2018 | 3 | 2018Q3 | 2.2515
48 | 4.197 | 2018 | 4 | 2018Q4 | 2.2515
49 | 1.687 | 2019 | 1 | 2019Q1 | 2.2515
50 | 2.657 | 2019 | 2 | 2019Q2 | 2.2515
51 | 2.402 | 2019 | 3 | 2019Q3 | 2.2515
52 | 1.099 | 2019 | 4 | 2019Q4 | 2.2515
53 | 1.037 | 2020 | 1 | 2020Q1 | 2.2515
54 | -0.243 | 2020 | 2 | 2020Q2 | 2.2515
55 | -1.393 | 2020 | 3 | 2020Q3 | 2.2515
56 | -1.619 | 2020 | 4 | 2020Q4 | 2.2515
57 | -1.857 | 2021 | 1 | 2021Q1 | 2.2515
58 | -0.672 | 2021 | 2 | 2021Q2 | 2.2515
59 | 3.2 | 2021 | 3 | 2021Q3 | 2.2515
60 | 5.144 | 2021 | 4 | 2021Q4 | 2.2515
61 | 6.716 | 2022 | 1 | 2022Q1 | 2.2515
62 | 10.141 | 2022 | 2 | 2022Q2 | 2.2515
63 | 9.438 | 2022 | 3 | 2022Q3 | 2.2515
64 | 9.088 | 2022 | 4 | 2022Q4 | 2.2515
65 | 8.243 | 2023 | 1 | 2023Q1 | 2.2515
66 | 4.813 | 2023 | 2 | 2023Q2 | 2.2515
67 | 4.077 | 2023 | 3 | 2023Q3 | 2.2515
68 | 3.583 | 2023 | 4 | 2023Q4 | 2.2515
69 | 3 | 2024 | 1 | 2024Q1 | 2.2515
70 | 2.456 | 2024 | 2 | 2024Q2 | 2.2515
71 | 2.251 | 2024 | 3 | 2024Q3 | 2.2515
72 | 3.257 | 2024 | 4 | 2024Q4 | 2.2515
73 | 3.743 | 2025 | 1 | 2025Q1 | 2.2515
74 | 4.119 | 2025 | 2 | 2025Q2 | 2.2515
75 | 3.676 | 2025 | 3 | 2025Q3 | 2.2515
76 | 3.573 | 2025 | 4 | 2025Q4 | 2.2515
77 | 3.523 | 2026 | 1 | 2026Q1 | 2.2515
78 | 3.193 | 2026 | 2 | 2026Q2 | 2.2515
79 | 3.757 | 2026 | 3 | 2026Q3 | 2.2515
80 | 3.197 | 2026 | 4 | 2026Q4 | 2.2515
81 | 3.715 | 2027 | 1 | 2027Q1 | 2.2515
82 | 3.738 | 2027 | 2 | 2027Q2 | 2.2515
83 | 3.729 | 2027 | 3 | 2027Q3 | 2.2515
84 | 3.526 | 2027 | 4 | 2027Q4 | 2.2515
85 | 3.602 | 2028 | 1 | 2028Q1 | 2.2515
86 | 3.671 | 2028 | 2 | 2028Q2 | 2.2515